## Sheet1
403 Validation Plan
Test Name | Success Criteria | Methodology | Status | Responsible:
Low RF Output (3.2.1.3) | RF output approximately 1.6GHz given 0.5 Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | COMPLETED | Brian Chau
High RF Output (3.2.1.3) | RF output approximately 3.2 GHz given (max) 20 Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | COMPLETED | Brian Chau
Modulation RF Output ( 3.2.1.3) | RF output oscillates between 1.6 to 3.2 GHz given periodic Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | IN PROGRESS | Brian Chau
Power Attenuator (3.2.1.2) | Simple circuit reduces VCO power output to 20dBm +/- 3dBm for RF amplifier. | Simple circuit tested on PCB and measured with voltmeter | COMPLETED | Brian Chau
RF Amplifier (3.2.1.4) | Amplifier produces RF output of 5V. | Use Oscilloscope to measure voltage | In PROGRESS | Brian Chau
Power Supply (3.2.3.1.1) | Power supply will provide correct voltage (3.6V) needed for each component (uControler, VCO, Amplifier) | Use Oscilloscope to measure voltage | COMPLETED | Eugene Asare
DC-DC Converter (3.2.3.1.2) | The converter with reviece a voltage from the 2 AA batteries that will be steped up to 24 V and 5.5 V for respective rails | Use Oscilloscope to measure voltage | COMPLETED | Eugene Asare
LDO (3.2.3.1.2) | Step down voltage from the DC-DC Converter to 3.3V and 5V | Use Oscilloscope to measure voltage and currents of each LDO | COMPLETED | Eugene Asare
Power Monitors Testing on PCB (3.2.3.1.2) | Each Power Monitor will record the volage and current inputs with the specific address assigned by the configuration | Use of all Components and PCB. | IN PROGRESS | Eugene Asare
LTSpice LDO Testing (3.2.3.1.2) | Each LDO will output the correct voltage. For the Digital Rail it will output 3.3 V with a 5.5 V input. For the VCO Rail it will output 5 V with a 5.5 V input. | Use LTSpice to simulate the LDO configuration by inputing 5.5 V into each LDO. | COMPLETED | Eugene Asare
LTSpice OpAmp Testing (3.2.3.1.2) | Differential OpAmp shall output correct voltage from 0-20V when input 1.8-3.6V on simulation software | Use LTSpice to simulate OpAmp configuration by inputting a controlled voltage from 1.8 to 3.6 into the OpAmp | COMPLETED | Daniel Hickl
Microcontroller MPLab Testing (3.2.3.2) | Microcontroller C code works as intended with 7 different states: Off, On: Constant Voltage, and On: Modulation. Within the On: Constant Voltage state, there shall be 5 different voltage outputs (5V, 10V, 15V, and 20V). Within the On: Modulation state, there shall be 3 different frequencies at which the voltage switches between 0V and 20V in a sawtooth waveform (1kHz, 5kHz, 10kHz) | Use MPLab to test code using interrupts to stop code. These shall be used to determine output voltages and frequencies | COMPLETED | Daniel Hickl
Microcontroller Evaluation Board Testing (3.2.3.2) | Test microcontroller code Using evaluation board. Same sucess criteria as MPLab Testing. Introduce DIP Switch and LEDs on breadboard to test states. | Use Evaluation Board to test different states of the Waveform Gererator | COMPLETED | Daniel Hickl
UART Connection testing ( 3.2.1.3) | The MCU shall write 5 lines of data to the computer | Connect UART cable to evaluation board and computer. Write 5 lines of data on UART bus for computer to capture on Serial Tool | COMPLETED | Daniel Hickl
I2C Connection testing ( 3.2.1.3) | The MCU shall recieve 5 lines of data from the I2C evaluation board. This data shall then be written to the connected computer using the UART connection | Connect UART cable and the I2C evaluation board to the MCU Evaluation board. Use Serial Tool to communicate this data with the evaluation board and write it to the computer using the UART connection. | COMPLETED | Daniel Hickl
MCU Testing on PCB (3.2.3.2) | Output of opamp shall be 0-20V and shall be able to modulate between 1kHz-10kHz. LED Shall light up when on. GUI shall communicate with MCU. Sensor shall communicate with MCU | Use of all Components and PCB. | COMPLETED | Daniel Hickl
Code Debug (3.2.3.2.1) | Code is able to compile, no major bug, GUI display correctly, perform fast, easily to use and read | Connect a COM port, compile code and run master script to use the GUI. | COMPLETED | Khoi Le
Reading Data (3.2.3.2.1) | the GUI will plot the voltage data to the channel window | Creat a test data file that represents the sensor output data. Then let the GUI read the files then plot them to the channel so the user can monitor the voltage. | COMPLETED | Khoi Le
GUI Sync Test (3.2.1.1) | Baud rate of GUI and microcontroller can sync correctly | Connect microconctroller to the USB com of computer, compile the GUI and it shows Sync Status is green | IN PROGRESS | Khoi Le
GUI edge case (3.2.1.1) | GUI throw error if it detects some invalid input, unable to make a connection via com port. | Make the edge case and observe the error showing on the monitor. | IN PROGRESS | Khoi Le
404 Validation Plan (System Integration)
Test Name | Success Criteria | Methodology | Status | Responsible:
Low RF Output (3.2.1.3) | RF output approximately 1.6GHz given 0.5 Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | UNTESTED | Brian Chau
High RF Output (3.2.1.3) | RF output approximately 3.2 GHz given (max) 20 Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | UNTESTED | Brian Chau
Modulation RF Output ( 3.2.1.3) | RF output oscillates between 1.6 to 3.2 GHz given periodic Vtune input. | Use Spectrum Analyzer (spectogram) and Oscilloscope to measure frequency output | UNTESTED | Brian Chau
RF Amplifier (3.2.1.4) | Amplifier produces RF output of 5V. | Use Oscilloscope to measure voltage | UNTESTED | Brian Chau
Power Supply (3.2.3.1.1) | Power supply will provide correct voltage current to each device. | Use Oscilloscope to measure voltage | UNTESTED | Eugene Asare
DC-DC Converter (3.2.3.1.2) | The converter with reviece a voltage from the 2 AA batteries that will be steped up to 24 V and 5.5 V for respective rails | Use Oscilloscope to measure voltage | UNTESTED | Eugene Asare
LDO (3.2.3.1.2) | Step down voltage from the DC-DC Converter to 3.3V and 5V | Use Oscilloscope to measure voltage and currents of each LDO | UNTESTED | Eugene Asare
Power Monitors Testing on PCB (3.2.3.1.2) | Each Power Monitor will record the volage and current inputs with the specific address assigned by the configuration | Use of all Components and PCB. | UNTESTED | Eugene Asare
MCU Analog Drive Testing | The MCU shall output a constant voltage from the DAC. This voltage shall be amplified anywhere in 0-20V range. | Use the DIP Switch parse through all the constant voltage states of the system. | UNTESTED | Daniel Hickl
MCU Analog Drive Testing | The MCU shall output a varying voltage (1kHz - 10kHz) from the DAC. This voltage shall be amplified anywhere in 0-20V range. | Use the DIP Switch parse through all the modulation states of the system. | UNTESTED | Daniel Hickl
I2C Connection testing ( 3.2.1.3) | The MCU shall recieve 5 lines of data from the sensor units via I2C. | Connect UART cable and the I2C evaluation board to the MCU Evaluation board. Use Serial Tool to communicate this data with the evaluation board and write it to the computer using the UART connection. | UNTESTED | Daniel Hickl
MCU Testing on PCB (3.2.3.2) | Output of opamp shall be 0-20V and shall be able to modulate between 1kHz-10kHz. LED Shall light up when on. GUI shall communicate with MCU. Sensor shall communicate with MCU | Use of all Components and PCB. | UNTESTED | Daniel Hickl
Reading Data (3.2.3.2.1) | the GUI will plot sensor voltage data to the channel window | After setting up communication between computer and MCU, let the GUI read the files output then plot them to the channel so the user can monitor the voltage. | UNTESTED | Khoi Le
GUI Sync Test (3.2.1.1) | Adjusting input voltage or baud rate | Connect microconctroller to the USB com of computer, compile the GUI and it shows Sync Status is green | UNTESTED | Khoi Le
GUI edge case (3.2.1.1) | GUI throw error if it detects some invalid input, unable to make a connection via com port. | Make the edge case and observe the error showing on the monitor. | UNTESTED | Khoi Le